## Summary
Removal Date | EagleNet User Group | Count of EagleNet Components
2019-04-26 |  | 1
2019-07-25 |  | 28
2019-08-23 |  | 1
2020-02-13 |  | 1
(empty) |  | 20
Fall 2020 |  | 12
2020-06-29 |  | 20
2021-01-01 |  | 4
| EagleNet for Faculty | 4
Total Result |  | 87

## TBD
EagleNet User Group | EagleNet Component | Removal Date | New Location | In MyHub Now | Notes
EagleNet for Employees - Prof Dev Registration | Grades |  | MyHub - HR/Employee | No | Professional Development credit type will need to be added to MyHub
EagleNet for Employees - Prof Dev Registration | My Class Schedule |  | MyHub - HR/Employee | No | Professional Development credit type will need to be added to MyHub
EagleNet for Faculty | My Advisees |  | MyHub - Advise | No | Link to Self Service or creation of widget
EagleNet for Faculty | Advisees |  | MyHub - Advise | No | Link to Self Service or creation of widget
EagleNet for Faculty | Class Roster w/Images |  | MyHub - Faculty | No | Link to Self Service or creation of widget
EagleNet for Faculty | Class Roster |  | MyHub - Faculty | No | Link to Self Service or creation of widget
EagleNet for Faculty | Grading |  | MyHub - Faculty | No | Link to Self Service or creation of widget - Sara checking with Dena on timeline
EagleNet for Faculty | My Class Schedule |  | MyHub - Faculty | No | Link to Self Service or creation of widget
EagleNet for Faculty | Student Planning for Faculty/Advisors |  | MyHub - Advise | No | Link to Self Service or creation of widget
EagleNet for Faculty | Student profile |  | NA | NA | Link to be deleted and not replaced
EagleNet for Faculty | Search for Sections - Informational purposes only |  | MyHub - Advise | No | When degree audit is turned on, turn this off in EagleNet
EagleNet for Advisors | My Advisees |  | MyHub - Advise | Yes | update url in MyHub to drop off at https://selfservice.kirkwood.edu/Student/Planning/Advisors
EagleNet for Advisors | Student Planning for Faculty/Advisors |  | MyHub - Advise | Yes | update url in MyHub to drop off at https://selfservice.kirkwood.edu/Student/Planning/Advisors
EagleNet for Advisors | Advisees |  | MyHub - Advise | No | update url in MyHub to drop off at https://selfservice.kirkwood.edu/Student/Planning/Advisors
EagleNet for Employees - Employee Profile | My Stipends |  | MyHub - HR/Employee | No | Link to Self Service - Needs to be turned on - Sara checking with lori
EagleNet for Employees - Employee Profile | Total Compensation |  | MyHub - HR/Employee | No | Link to Self Service - Needs to be turned on - Sara checking with lori
EagleNet for Employees - Employee Profile | Leave Plan Summary/Detail |  | MyHub - HR/Employee | No | If Ellucian can deliver within Self Service that will be used if not, a custom solution will be developed - Sara to check with Lori
EagleNet for Employees - Budget Information (Staff) | Budget Selection |  | MyHub - HR/Employee | No | Link to Self Service - Sara to follow up with Jon
EagleNet for Employees - Budget Information (Staff) | Budget Summary |  | MyHub - HR/Employee | No | Link to Self Service - Sara to follow up with Jon
EagleNet for Students - Registration | Search for Sections |  | MyHub - Search for Courses | Yes | When degree audit is turned on, turn this off in EagleNet
EagleNet for Students - Registration | Search/Register for Sections |  | MyHub - Search for Courses, Course Planner | Yes | When degree audit is turned on, turn this off in EagleNet
EagleNet for Students - Registration | Register and Drop Sections |  | MyHub - My Courses - Course Planner | Yes | When degree audit is turned on, turn this off in EagleNet
EagleNet for Students - Registration | Express Registration |  | N/A | NA | Link to be deleted and not replaced

## January 2021
EagleNet User Group | EagleNet Component | Removal Date | New Location | In MyHub Now | Notes
EagleNet for Employees - Time Entry and Approval | Time Entry | Fall 2020 | MyHub - HR/Employee | No | If Ellucian can deliver within Self Service that will be used if not, a custom solution will be developed
EagleNet for Employees - Time Entry and Approval | Time History | Fall 2020 | MyHub - HR/Employee | No | If Ellucian can deliver within Self Service that will be used if not, a custom solution will be developed
EagleNet for Employees - Time Entry and Approval | Time approval (for supervisors) | Fall 2020 | MyHub - HR/Employee | No | If Ellucian can deliver within Self Service that will be used if not, a custom solution will be developed
EagleNet for Employees - Time Entry and Approval | Employee History (for supervisors) | Fall 2020 | MyHub - HR/Employee | No | If Ellucian can deliver within Self Service that will be used if not, a custom solution will be developed

## Fall 2020
EagleNet User Group | EagleNet Component | Removal Date | New Location | In MyHub Now | Notes
EagleNet for Students - Academic Planning | Degree Audit | Fall 2020* | MyHub - Education - My Programs or My Courses | No | Ellucian will be contracted to build this functionality within Self Service
EagleNet for Students - Academic Profile | Degree Audit | Fall 2020* | MyHub - Education - My Programs or My Courses | No | Ellucian will be contracted to build this functionality within Self Service
EagleNet for Students - Academic Profile | My Transfer Equivalencies | Fall 2020* | MyHub - Education - My Programs or My Courses | No | This report will need to be accessible via MyHub and coordnated with implementation of Degree Audit
EagleNet for Advisors | Placement Scores & Course Recommendations |  | MyHub - Advise | Yes | Link to Self Service or creation of widget
EagleNet for Faculty | Placement Scores & Course Recommendations |  | MyHub - Advise | Yes | Link to Self Service or creation of widget
EagleNet for Students - Financial Information | Course Payment Verification Request |  | MyHub - My Courses | Yes | The existing Reporting Services report will be added to MyHub

## June 29 2020
EagleNet User Group | EagleNet Component | Removal Date | New Location | In MyHub Now | Notes
EagleNet for Students - Financial Information | Set up Payment Plan | 2020-06-29 | MyHub - Billing & Payments | Yes | A solution to pass the personal key to TouchNet will be required
EagleNet for Students - Financial Information | Direct Deposit | 2020-06-29 | MyHub - Billing & Payments | Yes | A solution to pass the personal key to TouchNet will be required
EagleNet for Students - Registration | Manage My Waitlist | 2020-06-29 | Self Service | Yes | The link will be added to Self Service
EagleNet for Students - Registration | Waitlist FAQ | 2020-06-29 | Self Service | Yes | Addition to MyHub FAQ
EagleNet for Students - Registration | Financial Aid and Enrollment Forms | 2020-06-29 | MyHub - Financial Aid Widget/Page | Yes | New widget/page will be created in MyHub
EagleNet for Students - Academic Planning | First Steps to College | 2020-06-29 | MyHub - Help | Yes | Addition to MyHub FAQ
EagleNet for Students - Academic Planning | Student FAQ | 2020-06-29 | MyHub - Help | Yes | Addition to MyHub FAQ
EagleNet for Students - Academic Planning | Apply for Graduation | 2020-06-29 | MyHub - Education - My Programs | Yes | Link to Self Service
EagleNet for Students - Academic Profile | Enrollment Verification Request | 2020-06-29 | MyHub - Education - My Courses | Yes | Link to Self Service but SSN needs to be masked - Needs to be enabled in Self Servcie
EagleNet for Students - Academic Profile | Enrollment Verification Request Status | 2020-06-29 | MyHub - Education - My Courses | Yes | Link to Self Service but SSN needs to be masked - Needs to be enabled in Self Servcie
EagleNet for Students - Academic Profile | National Clearinghouse | 2020-06-29 | MyHub - Financial Aid Widget/Page | Yes | New widget/page will be created in MyHub
EagleNet for Employees - User Account | Change Password | 2020-06-29 | Login Screen - MyHub | Yes
EagleNet for Employees - User Account | Establish My Password | 2020-06-29 | Login Screen - MyHub | Yes
EagleNet for Employees - User Account | Forgot My Password | 2020-06-29 | Login Screen - MyHub | Yes
EagleNet for Employees - User Account | k Number Information | 2020-06-29 | Login Screen - MyHub | Yes
EagleNet for Employees - Employee Profile | Rental Car Reservations | 2020-06-29 | MyHub - Favorite Links | Yes | Link to reservation system
EagleNet for Employees - Employee Profile | W-2 Electronic Consent | 2020-06-29 | MyHub - HR/Employee | Yes | Link to Self Service
EagleNet for Employees - Employee Profile | W-2 Statements | 2020-06-29 | MyHub - HR/Employee | Yes | Link to Self Service
EagleNet for Employees - Employee Profile | Earning Statements (Pay Advices) | 2020-06-29 | MyHub - HR/Employee | Yes | Link to Self Service

## May 29 2020
EagleNet User Group | EagleNet Component | Removal Date | New Location | In MyHub Now | Notes
EagleNet for Employees - User Account | Address or Phone Number Change | 2020-05-29 | MyHub - Profile | Yes | Available in realtime update in January 2020

## April 26 2019
EagleNet User Group | EagleNet Component | Removal Date | New Location | In MyHub Now | Notes
EagleNet for Students - Communication | International Student Portal | 2019-04-26 | NA | NA | This link was not functional and has been removed from EagleNet

## July 25 2019
EagleNet User Group | EagleNet Component | Removal Date | New Location | In MyHub Now | Notes
EagleNet for Students - User Account Menu | Address or phone Number Change | 2019-07-25 | MyHub - Account Information | Yes
EagleNet for Students - User Account Menu | Change Password | 2019-07-25 | MyHub - Login Screen | Yes
EagleNet for Students - User Account Menu | Establish My Password | 2019-07-25 | MyHub - Login Screen | Yes
EagleNet for Students - User Account Menu | Forgot My Password | 2019-07-25 | MyHub - Login Screen | Yes
EagleNet for Students - User Account Menu | K number Information | 2019-07-25 | MyHub - Login Screen | Yes
EagleNet for Students - User Account Menu | Self Service | 2019-07-25 | MyHub - Various: Search Course Catalog, Financial Aid - Check Status, Account Summary - MyBill - Account Activity. 1098T, W-2 | Yes
EagleNet for Students - User Account Menu | Not Anymore: Gender Violence | 2019-07-25 | MyHub - All Links - Resources | Yes
EagleNet for Students - Financial Information | My Kirkwood Bill By Term | 2019-07-25 | MyHub - Account Summary - My Bill - Account Activity | Yes
EagleNet for Students - Financial Information | Make A Payment | 2019-07-25 | MyHub - Account Summary - My Bill - Pay Bill & Info Icon | Yes
EagleNet for Students - Financial Information | Setting Up an Authorized User | 2019-07-25 | NA | NA | Link to be deleted and not replaced
EagleNet for Students - Financial Information | FAQs - 1098T Tax Forms | 2019-07-25 | MyHub - Account Summary - My Bill - 1098T | Yes
EagleNet for Students - Financial Information | Tax Information | 2019-07-25 | NA | NA | Link to be deleted and not replaced
EagleNet for Students - Financial Aid | Financial Aid Checklist | 2019-07-25 | MyHub - Check Status | Yes
EagleNet for Students - Financial Aid | My Available Bookstore Funds | 2019-07-25 | MyHub - Account Summary - Bookstore Funds | Yes
EagleNet for Students - Financial Aid | Financial Aid Shopping Sheet | 2019-07-25 | Moved to Self Service | NA | Shopping Sheet will be created in Self Service
EagleNet for Students - Academic Planning | Student Planning | 2019-07-25 | MyHub - View My Courses - Course Planner | Yes
EagleNet for Students - Academic Planning | Schedule and Plan your Courses Help | 2019-07-25 | MyHub - Help- Registration- Search and register for classes | Yes
EagleNet for Students - Academic Planning | Placement Scores and Recommendations | 2019-07-25 | MyHub - Education - Placement Scores | Yes
EagleNet for Students - Academic Profile | My Grades | 2019-07-25 | MyHub - MyCourses | Yes
EagleNet for Students - Academic Profile | View My Kirkwood Transcript | 2019-07-25 | MyHub - My Courses - Course Planner - Unoffical Transcript | Yes
EagleNet for Students - Academic Profile | Test Summary | 2019-07-25 | MyHub - Education - Placement Scores | Yes
EagleNet for Students - Academic Profile | Transcript Request | 2019-07-25 | MyHub - My Courses - Send Transcript | Yes
EagleNet for Students - Academic Profile | My Class Schedule | 2019-07-25 | MyHub - My Schedule | Yes
EagleNet for Students - Academic Profile | My Profile | 2019-07-25 | MyHub - My Account | Yes
EagleNet for Students - Academic Profile | Online Bookstore | 2019-07-25 | MyHub - Student Links - Resources | Yes
EagleNet for Students - Communication | My Kirkwood Documents | 2019-07-25 | NA | NA | Link to be deleted and not replaced
EagleNet for Employees - User Account | Self Service | 2019-07-25 | NA | NA | Link to be deleted and not replaced
EagleNet for Employees - User Account | Not Anymore: Gender Violence Prevention Requirement | 2019-07-25 | NA | NA | Link to be deleted and not replaced
EagleNet for Employees - Communication | My Kirkwood Documents | 2019-07-25 | NA | NA | This link was not functional and will be removed from EagleNet

## August 23 2019
EagleNet User Group | EagleNet Component | Removal Date | New Location | In MyHub Now | Notes
EagleNet for Students - Registration | Student Consent | 2019-08-23 | Self Service | NA | This popup will occur during planning & registration in Self Service

## Communication Plan
Communication Plan |  | )
Task | Assignee | Audience | Target Date | Completion Date | Completed | Notes
Meeting with Jon | Sara/Justin |  | 2019-06-04 | 2019-06-04 | Yes
Get on Academic Affairs Agenda | Sara | Academic Affairs | 2019-06-07 | 2019-07-10 | Yes | Have Communication plan so that they can distribute to Deans, Faculty and Staff
Email as head up about communication coming out | Sara | Kris Riley/Sue Bennett, Deb Wilson | 2019-06-07 | 2019-06-05 | Yes
Schedule Meeting with Nate, Kathy and Carrie as heads up about EagleNet plan | Sara | Service Desk/Student Help Desk | 2019-06-07 | 2019-06-25 | Yes | Scheduled first week of July.
Meet with Mike to determine owners of pages with EagleNet content | Sara |  | 2019-06-07 | 2019-06-05 | Yes | So that when we send email out to stakeholders we can inlcude what pages need to be updated
Meet with Mike to create web page to display communication of timeline | Sara |  | 2019-06-07 | 2019-07-09 | Yes | Created a KIN Site folder for this
Create Tasks in Jira for MyHub enhancements | Justin/Adam |  | 2019-06-14
Meeting with Marketing to share communication plan & timeline | Sara | Tierney Hein, Kevin Hansen | 2019-06-14 | 2019-06-25 | Yes | Present Mike's list, know that printed documents will need to be updated also. Scheduled first week of July.
Meeting with Danielle to discuss Budgeting in Self Service | Lori |  | 2019-07-18 |  |  | Jon has seen the budgeting module and really likes it. Schedule meeting with Danielle after FY activities are completed.
Create TD Tickets for all of Lori's tasks | Sara |  | 2019-06-27 | 2019-06-26 | Yes | Done, for all the 2019 tasks. 2020 tasks will come later.
Lori to create message on EagleNet with link to webpage | Sara/Lori |  | 2019-07-01 | 2019-07-25 | Yes
Email to all colleague users | Sara | Colleague UI users | 2019-07-01 |  |  | Communicate timeline and where links can be found
Meet with Advising Group | Sara | (Melissa/Bobbi/others
Meet with small Dean Group | Sara | Brooke/Scott/Jennifer Bradley
Meet with HR | Justin | HR team | 2019-07-10 | 2019-07-30 | Yes
Email to stakeholders with Communication Plan and Timeline | Sara | Kris Riley, Jamie Lehmkuhl, Matt Falduto, Bridget Dusek, Patrick Clemence, Dena Rauch, Sue Bennett, Deb Wilson, Wes Fowler, Melissa Payne, Bobbi Miller | 2019-07-10
Month of each release - Have You Heard each week as reminder | Sara | College Wide | Various

## DPCache_Master Timeline (hidden)
EagleNet User Group | EagleNet Component | Removal Date | New Location | In MyHub Now | Notes
EagleNet for Students Menu
EagleNet for Students - Communication | International Student Portal | 2019-04-26 | NA | NA | This link was not functional and has been removed from EagleNet
EagleNet for Students - User Account Menu | Address or phone Number Change | 2019-07-25 | MyHub - Account Information | Yes | Done.
EagleNet for Students - User Account Menu | Change Password | 2019-07-25 | MyHub - Login Screen | Yes
EagleNet for Students - User Account Menu | Establish My Password | 2019-07-25 | MyHub - Login Screen | Yes
EagleNet for Students - User Account Menu | Forgot My Password | 2019-07-25 | MyHub - Login Screen | Yes
EagleNet for Students - User Account Menu | K number Information | 2019-07-25 | MyHub - Login Screen | Yes
EagleNet for Students - User Account Menu | Self Service | 2019-07-25 | MyHub - Various: Search Course Catalog, Financial Aid - Check Status, Account Summary - MyBill - Account Activity. 1098T, W-2 | Yes
EagleNet for Students - User Account Menu | Not Anymore: Gender Violence | 2019-07-25 | MyHub - All Links - Resources | Yes
EagleNet for Students - Financial Information | My Kirkwood Bill By Term | 2019-07-25 | MyHub - Account Summary - My Bill - Account Activity | Yes
EagleNet for Students - Financial Information | Make A Payment | 2019-07-25 | MyHub - Account Summary - My Bill - Pay Bill & Info Icon | Yes
EagleNet for Students - Financial Information | Setting Up an Authorized User | 2019-07-25 | NA | NA | Link to be deleted and not replaced
EagleNet for Students - Financial Information | FAQs - 1098T Tax Forms | 2019-07-25 | MyHub - Account Summary - My Bill - 1098T | Yes
EagleNet for Students - Financial Information | Tax Information | 2019-07-25 | NA | NA | Link to be deleted and not replaced
EagleNet for Students - Financial Aid | Financial Aid Checklist | 2019-07-25 | MyHub - Check Status | Yes
EagleNet for Students - Financial Aid | My Available Bookstore Funds | 2019-07-25 | MyHub - Account Summary - Bookstore Funds | Yes
EagleNet for Students - Financial Aid | Financial Aid Shopping Sheet | 2019-07-25 | Moved to One Stop page | No | Shopping Sheet will be created in Self Service and linked from the One Stop page http://www.kirkwood.edu/onestopforms
EagleNet for Students - Academic Planning | Student Planning | 2019-07-25 | MyHub - View My Courses - Course Planner | Yes
EagleNet for Students - Academic Planning | Schedule and Plan your Courses Help | 2019-07-25 | MyHub - Help- Registration- Search and register for classes | Yes
EagleNet for Students - Academic Planning | Placement Scores and Recommendations | 2019-07-25 | MyHub - Education - Placement Scores | Yes
EagleNet for Students - Academic Profile | My Grades | 2019-07-25 | MyHub - MyCourses | Yes
EagleNet for Students - Academic Profile | View My Kirkwood Transcript | 2019-07-25 | MyHub - My Courses - Course Planner - Unoffical Transcript | Yes
EagleNet for Students - Academic Profile | Test Summary | 2019-07-25 | MyHub - Education - Placement Scores | Yes
EagleNet for Students - Academic Profile | My Class Schedule | 2019-07-25 | MyHub - My Schedule | Yes
EagleNet for Students - Academic Profile | My Profile | 2019-07-25 | MyHub - My Account | Yes
EagleNet for Students - Academic Profile | Online Bookstore | 2019-07-25 | MyHub - Student Links - Resources | Yes
EagleNet for Students - Communication | My Kirkwood Documents | 2019-07-25 | NA | NA | Link to be deleted and not replaced
EagleNet for Employees - User Account | Self Service | 2019-07-25 | NA | NA | Link to be deleted and not replaced
EagleNet for Employees - User Account | Not Anymore: Gender Violence Prevention Requirement | 2019-07-25 | NA | NA | Link to be deleted and not replaced
EagleNet for Employees - Communication | My Kirkwood Documents | 2019-07-25 | NA | NA | This link was not functional and will be removed from EagleNet
EagleNet for Students - Registration | Student Consent | 2019-08-23 | Self Service | No | This popup will occur during planning & registration in Self Service
EagleNet for Students - Academic Profile | Transcript Request | 2020-02-13 | MyHub - My Courses - Send Transcript | Yes
EagleNet for Students - Registration | Manage My Waitlist | 2020-06-29 | Self Service | Yes | The link will be added to Self Service
EagleNet for Students - Registration | Waitlist FAQ | 2020-06-29 | Self Service | Yes | The link will be added to Self Service
EagleNet for Students - Registration | Financial Aid and Enrollment Forms | 2020-06-29 | MyHub - Financial Aid Widget/Page | No | New widget/page will be created in MyHub
EagleNet for Students - Financial Information | Set up Payment Plan | 2020-06-29 | MyHub - Account Summary | Yes | A solution to pass the personal key to TouchNet will be required
EagleNet for Students - Financial Information | Direct Deposit | 2020-06-29 | MyHub - Account Summary | Yes | A solution to pass the personal key to TouchNet will be required
EagleNet for Students - Academic Profile | Enrollment Verification Request | 2020-06-29 | MyHub - Education - My Courses | Yes | Link to Self Service but SSN needs to be masked - Needs to be enabled in Self Service
EagleNet for Students - Academic Profile | Enrollment Verification Request Status | 2020-06-29 | MyHub - Education - My Courses | Yes | Link to Self Service but SSN needs to be masked - Needs to be enabled in Self Service
EagleNet for Students - Academic Profile | National Clearinghouse | 2020-06-29 | MyHub - Financial Aid Widget/Page | No | New widget/page will be created in MyHub
EagleNet for Students - Academic Planning | First Steps to College | 2020-06-29 | MyHub - Help | No | Addition to MyHub FAQ
EagleNet for Students - Academic Planning | Student FAQ | 2020-06-29 | MyHub - Help | No | Addition to MyHub FAQ
EagleNet for Students - Academic Planning | Apply for Graduation | 2020-06-29 | MyHub - Education - My Programs | No | Link to Self Service
EagleNet for Students - Registration | Search/Register for Sections | Fall 2020 | MyHub - Search for Courses, Course Planner | Yes
EagleNet for Students - Registration | Register and Drop Sections | Fall 2020 | MyHub - My Courses - Course Planner | Yes
EagleNet for Students - Registration | Express Registration | Fall 2020 | N/A | NA | Link to be deleted and not replaced
EagleNet for Students - Registration | Search for Sections | Fall 2020 | MyHub - Search for Courses | Yes
EagleNet for Students - Financial Information | Course Payment Verification Request | Fall 2020 | MyHub - My Courses | No | The existing Reporting Services report will be added to MyHub
EagleNet for Students - Academic Profile | Degree Audit | Fall 2020 | MyHub - Education - My Programs or My Courses | No | Ellucian will be contracted to build this functionality within Self Service
EagleNet for Students - Academic Planning | Degree Audit | Fall 2020 | MyHub - Education - My Programs or My Courses | No | Ellucian has been contracted to build this functionality within Self Service
EagleNet for Students - Academic Profile | My Transfer Equivalencies | Fall 2020 | MyHub - Education - My Programs or My Courses | No | This report will need to be accessible via MyHub and coordnated with implementation of Degree Audit
EagleNet for Employees Menu
EagleNet for Employees - User Account | Change Password | 2020-06-29 | Login Screen - MyHub | Yes
EagleNet for Employees - User Account | Establish My Password | 2020-06-29 | Login Screen - MyHub | Yes
EagleNet for Employees - User Account | Forgot My Password | 2020-06-29 | Login Screen - MyHub | Yes
EagleNet for Employees - User Account | k Number Information | 2020-06-29 | Login Screen - MyHub | Yes
EagleNet for Employees - User Account | Address or Phone Number Change | 2020-06-29 | MyHub - Account | Yes | Available in real-time updates starting in January 2020
EagleNet for Employees - Employee Profile | Rental Car Reservations | 2020-06-29 | MyHub - Favorite Links | Yes | Link to reservation system
EagleNet for Employees - Employee Profile | Earning Statements (Pay Advices) | 2020-06-29 | MyHub - HR/Employee | Yes | Link to Self Service
EagleNet for Employees - Employee Profile | W-2 Electronic Consent | 2020-06-29 | MyHub - HR/Employee | Yes | Link to Self Service
EagleNet for Employees - Employee Profile | W-2 Statements | 2020-06-29 | MyHub - HR/Employee | Yes | Link to Self Service
EagleNet for Employees - Time Entry and Approval | Time Entry | Fall 2020 | MyHub - HR/Employee | No | If Ellucian can deliver within Self Service that will be used if not, a custom solution will be developed
EagleNet for Employees - Time Entry and Approval | Time History | Fall 2020 | MyHub - HR/Employee | No | If Ellucian can deliver within Self Service that will be used if not, a custom solution will be developed
EagleNet for Employees - Time Entry and Approval | Time approval (for supervisors) | Fall 2020 | MyHub - HR/Employee | No | If Ellucian can deliver within Self Service that will be used if not, a custom solution will be developed
EagleNet for Employees - Time Entry and Approval | Employee History (for supervisors) | Fall 2020 | MyHub - HR/Employee | No | If Ellucian can deliver within Self Service that will be used if not, a custom solution will be developed
EagleNet for Employees - Prof Dev Registration | Grades |  | MyHub - HR/Employee | No | Professional Development credit type will need to be added to MyHub
EagleNet for Employees - Prof Dev Registration | My Class Schedule |  | MyHub - HR/Employee | No | Professional Development credit type will need to be added to MyHub
EagleNet for Employees - Prof Dev Registration | Search for Professional Development Classes |  | MyHub - HR/Employee | No | This will need to be restricted to employee's only with MyHub
EagleNet for Employees - Employee Profile | My Stipends |  | MyHub - HR/Employee | No | Link to Self Service - Needs to be turned on
EagleNet for Employees - Employee Profile | Total Compensation |  | MyHub - HR/Employee | No | Link to Self Service - Needs to be turned on
EagleNet for Employees - Employee Profile | Leave Plan Summary/Detail |  | MyHub - HR/Employee | No | If Ellucian can deliver within Self Service that will be used if not, a custom solution will be developed
EagleNet for Employees - Employee Profile | Position Summary |  | MyHub - HR/Employee | No | If Ellucian can deliver within Self Service that will be used if not, a custom solution will be developed
EagleNet for Employees - Budget Information (Staff) | Budget Selection |  | MyHub - HR/Employee | No | Link to Self Service
EagleNet for Employees - Budget Information (Staff) | Budget Summary |  | MyHub - HR/Employee | No | Link to Self Service
EagleNet for Faculty Menu
EagleNet for Faculty | Class Roster w/Images | 2021-01-01 | MyHub - Faculty | No | Link to Self Service or creation of widget
EagleNet for Faculty | Class Roster | 2021-01-01 | MyHub - Faculty | No | Link to Self Service or creation of widget
EagleNet for Faculty | My Class Schedule | 2021-01-01 | MyHub - Faculty | No | Link to Self Service or creation of widget
EagleNet for Faculty | Grading | 2021-01-01 | MyHub - Faculty | No | Link to Self Service or creation of widget
EagleNet for Faculty | Student Planning for Faculty/Advisors |  | MyHub - Advise | No | Link to Self Service or creation of widget
EagleNet for Faculty | Student profile |  | NA | NA | Link to be deleted and not replaced
EagleNet for Faculty | My Advisees |  | MyHub - Advise | No | Link to Self Service or creation of widget
EagleNet for Faculty | Advisees |  | MyHub - Advise | No | Link to Self Service or creation of widget
EagleNet for Faculty | Placement Scores & Course Recommendations |  | MyHub - Advise | No | Link to Self Service or creation of widget - will go in next build.
EagleNet for Faculty | Search for Sections - Informational purposes only |  | MyHub - Advise | No | Link to Self Service or creation of widget
EagleNet For Advisors Menu
EagleNet for Advisors | My Advisees |  | MyHub - Advise | No | Link to Self Service or creation of widget
EagleNet for Advisors | Student Planning for Faculty/Advisors |  | MyHub - Advise | No | Link to Self Service or creation of widget
EagleNet for Advisors | Advisees |  | MyHub - Advise | No | Link to Self Service or creation of widget
EagleNet for Advisors | Placement Scores & Course Recommendations |  | MyHub - Advise | No | Link to Self Service or creation of widget
EagleNet for Advisors | Search for Sections - Informational purposes only |  | MyHub - Advise | No | Link to Self Service or creation of widget